## Enrolment
Site | Site Name | Month | Target | Enrolled | Screen Failures | Notes
Site A | King's College Hospital | January 2026 | 8 | 7 | 2
Site A | King's College Hospital | February 2026 | 8 | 5 | 4 | Lead coordinator on annual leave wk2-3
Site A | King's College Hospital | March 2026 | 8 | 8 | 1
Site B | Manchester Royal Infirmary | January 2026 | 6 | 2 | 8 | Capacity issues flagged by PI
SiteB | Manchester Royal Infirmary | February 2026 | 6 | 3 | 9
Site B | Manchester Royal Infirmary | March 2026 | 6 | 2 | 7 | PI considering withdrawing
Site C | Bristol Royal Infirmary | January 2026 | 5 | 5 | 1
Site C | Bristol Royal Infirmary | February 2026 |  | 6 | 0 | Over-enrolled - capacity expanded
Site C | Bristol Royal Infirmary | March 2026 | 5 | 4 | 2
Site D | Leeds General Infirmary | February 2026 | 7 | 7 | 3
Site D | Leeds General Infirmary | March 2026 | 7 | 6 | 2
Site E | Edinburgh Royal Infirmary | January 2026 | 6 | 6 | 14 | Eligibility criteria queries raised
Site E | Edinburgh Royal Infirmary | February 2026 | 6 | 5 | 12
Site E | Edinburgh Royal Infirmary | March 2026 | 6 | 6 | 15 | Protocol deviation query submitted

## SDV & Quality
Site ID | Hospital | Period | Queries Open | Queries >14d | SDV Complete (%) | Protocol Deviations | Last Monitoring Visit
A | King's College Hospital | Jan-26 | 3 | 0 | 0.94 | 0 | 12-Jan-26
A | King's College Hospital | Feb-26 | 5 | 2 | 0.88 | 1 | 12-Jan-26
A | King's College Hospital | Mar-26 | 2 | 0 | 0.97 | 0 | 15-Mar-26
B | Manchester Royal Infirmary | Jan-26 | 11 | 6 | 0.61 | 3 | 08-Jan-26
B | Manchester Royal Infirmary | Feb-26 | 14 | 9 | 0.55 | 4 | 08-Jan-26
B | Manchester Royal Infirmary | Mar-26 | 18 | 12 | 0.48 | 5 | 08-Jan-26
C | Bristol Royal Infirmary | Jan-26 | 1 | 0 | 0.99 | 0 | 20-Jan-26
C | Bristol Royal Infirmary | Feb-26 | 2 | 0 | 0.98 | 0 | 19-Feb-26
C | Bristol Royal Infirmary | Mar-26 | 1 | 0 | 0.99 | 0 | 18-Mar-26
D | Leeds General Infirmary | Jan-26
D | Leeds General Infirmary | Feb-26 | 4 | 1 | 0.91 | 1 | 03-Feb-26
D | Leeds General Infirmary | Mar-26 | 3 | 0 | 0.93 | 0 | 04-Mar-26
E | Edinburgh Royal Infirmary | Jan-26 | 7 | 3 | 79 | 2 | 15-Jan-26
E | Edinburgh Royal Infirmary | Feb-26 | 9 | 4 | 81 | 1 | 14-Feb-26
E | Edinburgh Royal Infirmary | Mar-26 | 8 | 5 | 76 | 3 | 12-Mar-26

## Trial Overview
Parameter | Value
Trial name | CARDINAL
Sponsor | Hartwell Therapeutics
Indication | Moderate-to-severe hypertension
Target total enrolment | 120
Number of sites | 5
Trial start date | 01-Nov-25
Target enrolment completion date | 31-Jul-26
Enrolment completed to date (end Mar 2026) | 72
Months remaining to enrolment completion | 4
Patients still to enrol | 48
Required monthly run rate to complete on time | 12

## Site Contacts
Site Ref | Site Name | Principal Investigator | Coordinator | Coordinator Email | Site Status | Date Activated | Notes
Site A | King's College Hospital | Dr. Sarah Okafor | James Patel | j.patel@kch.nhs.uk | Active | 15-Nov-25 | Strong recruiter historically. PI recently took on additional study.
Site B | Manchester Royal Infirmary | Prof. David Leigh | Emma Thornton | e.thornton@mri.nhs.uk | Active - at risk | 01-Nov-25 | New to Lindus trials. Study coordinator changed in February.
Site C | Bristol Royal Infirmary | Dr. Priya Nair | Tom Williams | t.williams@bri.nhs.uk | Active | 10-Nov-25 | Consistently high performer. Very experienced team.
Site D | Leeds General Infirmary | Dr. Mark Hassan | Fatima Al-Rashid | f.alrashid@lgi.nhs.uk | Active | 28-Jan-26 | High screen failure rate noted from initiation. Possible patient population mismatch with inclusion criteria.
Site E | Edinburgh Royal Infirmary | Prof. Fiona McGrath | Callum Steele | c.steele@eri.nhs.uk | Active | 01-Nov-25 | Previously strong recruiter. Coordinator on extended leave from March.